## accessibility-audit-template
issue_id | page_or_component | wcag_reference | evidence | severity | user_impact | recommended_fix | owner | status
WEB-003 | myScheme Accessibility Widget | WCAG 2.4.3 — Focus Order | Lighthouse flagged multiple buttons with positive tabindex values (1–8), including Bigger Text, Smaller Text, and Text Spacing. | Medium | Keyboard and assistive-technology users may experience an unexpected focus order. | Replace positive tabindex values with tabindex="0" where needed, or remove tabindex when native button behavior is sufficient. Verify the intended focus order with keyboard testing. | Student | Open
WEB-004 | myScheme Language Selector | WCAG 2.1.1 — Keyboard (potential issue; verify) | Mouse opens the language menu, but during keyboard testing, focus moved from Sign In directly to the light-mode button without visibly focusing the English selector. | Medium | Keyboard users may have difficulty accessing the language selector | Ensure the language selector can receive keyboard focus and be operated with Enter/Space, with a visible focus indicator. | Student | Open
WEB-005 | myScheme Search Field | WCAG 1.4.3 — Contrast (Minimum) | Lighthouse flagged the search field placeholder “Enter scheme name to search...” for insufficient foreground/background contrast. | Medium | Users with low vision may have difficulty reading the search placeholder text. | Adjust the text and background colors to meet WCAG contrast requirements: 4.5:1 for normal text and 3:1 for large text. | Student | Open
WEB-006 | Footer — Useful Links | WCAG 2.1.1 — Keyboard | DigiLocker and UMANG logos open links when clicked with a mouse, but keyboard Tab navigation did not visibly focus these links. | Medium | Keyboard users may be unable to access the external Useful Links. | Ensure interactive logo links are keyboard-focusable and show a visible focus indicator. | Student | Open
WEB-007 | myScheme Chatbot | WCAG 2.1.1 – Keyboard | Chatbot opens with mouse click, but keyboard Tab navigation did not visibly focus the chatbot trigger. | Medium | Keyboard-only users may be unable to open the chatbot. | Ensure the chatbot trigger is keyboard-focusable, supports Enter/Space, and displays a visible focus indicator. | Student | Open